## Sheet1
Side 1 | Side 2 | Category
4. Project Integration Management: processes | 4.1. Develop project charter 4.2. Develop project management plan 4.3. Direct and manage project work 4.4. Manage project knowledge 4.5. Monitor and control project work 4.6. Perform integrated change control 4.7. Close project or phase
4.1. Develop Project Charter: inputs | 1. Business documents (business case) 2. Agreements 3. Enterprise environmental factors 4. Organizational process assets
4.1. Develop Project Charter: tools and techniques | 1. Expert judgment 2. Data gathering (brainstorming, focus groups, interviews) 3. Interpersonal and team skills (conflict management, facilitation, meeting management) 4. Meetings
4.1. Develop Project Charter: outputs | 1. Project charter 2. Assumption log
4.2. Develop Project Management Plan: inputs | 1. Project charter 2. Outputs from other processes 3. Enterprise environmental factors 4. Organizational process assets
4.2. Develop Project Management Plan: tools and techniques | 1. Expert judgment 2. Data gathering (brainstorming, checklists, focus groups, interviews) 3. Interpersonal and team skills (conflict management, facilitation, meeting management) 4. Meetings
4.2. Develop Project Management Plan: outputs | 1. Project management plan
4.3. Direct and Manage Project Work: inputs | 1. Project management plan 2. Project documents (change log, lessons learned register, milestone list, project communications, project schedule, requirements traceability matrix, risk register, risk report) 3. Approved change requests 4. Enterprise environmental factors 5. Organizational process assets
4.3. Direct and Manage Project Work: tools and techniques | 1. Expert judgment 2. Project management information system 3. Meetings
4.3. Direct and Manage Project Work: outputs | 1. Deliverables 2. Work performance data 3. Issue log 4. Change requests 5. Project management plan updates 6. Project documents updates (activity list, assumption log, lessons learned register, requirements documentation, risk register, stakeholder register) 7. Organizational process assets updates
4.4. Manage Project Knowledge: inputs | 1. Project management plan 2. Project documents (lessons learned register, project team assignments, resource breakdown structure, stakeholder register) 3. Deliverables 4. Enterprise environmental factors 5. Organizational process assets
4.4. Manage Project Knowledge: tools and techniques | 1. Expert judgment 2. Knowledge management 3. Information management 4. Interpersonal and team skills
4.4. Manage Project Knowledge: outputs | 1. Lessons learned register 2. Project management plan updates 3. Organizational process assets updates
4.5. Monitor and Control Project Work: inputs | 1. Project management plan 2. Project documents (assumption log, basis of estimates, cost forecasts, issue log, lessons learned register, milestone list, quality reports, risk register, risk report, schedule forecasts) 3. Work performance information 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets
4.5. Monitor and Control Project Work: tools and techniques | 1. Expert judgment 2. Data analysis (alternatives analysis, cost-benefit analysis, earned value analysis, root cause analysis, trend analyais, variance analysis) 3. Decision making 4. Meetings
4.5. Monitor and Control Project Work: outputs | 1. Work performance reports 2. Change requests 3. Project management plan updates 4. Project documents updates (cost forecasts, issue log, lessons learned register, risk register, schedule forecasts)
4.6. Perform Integrated Change Control: inputs | 1. Project management plan (change management plan, configuration management plan, scope baseline, schedule baseline, cost baseline) 2. Project documents (basis of estimates, requirements traceability matrix, risk report) 3. Work performance reports 4. Change requests 5. Enterprise environmental factors 6. Organizational process assets
4.6. Perform Integrated Change Control: tools and techniques | 1. Expert judgment 2. Change control tools 3. Data analysis (alternatives analysis, cost-benefit analysis) 4. Decision making 5. Meetings
4.6. Perform Integrated Change Control: outputs | 1. Approved change requests 2. Project management plan updates 3. Project documents updates (change log)
4.7. Close Project or Phase: inputs | 1. Project charter 2. Project management plan 3. Project documents (assumption log, basis of estimates, change log, issue log, lessons learned register, milestone list, project communications, quality control measurements, quality reports, requirements documentation, risk register, risk report) 4. Accepted deliverables 5. Business documents (business case, benefits management plan) 6. Agreements 7. Procurement documentation 8. Organizational process assets
4.7. Close Project or Phase: tools and techniques | 1. Expert judment 2. Data analysis (document analysis, regression analysis, trend analysis, variance analysis) 3. Meetings
4.7. Close Project or Phase: outputs | 1. Project documents updates 2. Final product, service, or result transition 3. Final report 4. Organizational process assets updates
5. Project Scope Management: processes | 5.1. Plan scope management 5.2. Collect requirements 5.3. Define scope 5.4. Create WBS 5.5. Validate scope 5.6. Control scope
5.1. Plan Scope Management: inputs | 1. Project charter 2. Project management plan (quality management plan, project life cycle description, development approach) 3. Enterprise and environmental factors 4. Organizational process assets
5.1. Plan Scope Management: tools and techniques | 1. Expert judgment 2. Data analysis (alternatives analysis) 3. Meetings
5.1. Plan Scope Management: outputs | 1. Scope management plan 2. Requirements management plan
5.2. Collect Requirements: inputs | 1. Project charter 2. Project management plan (scope management plan, requirements management plan, stakeholder management plan) 3. Project documents (assumption log, lessons learned register, stakeholder register) 4. Business documents (business case) 5. Agreements 6. Enterprise environmental factors 7. Organizational process assets
5.2. Collect Requirements: tools and techniques | 1. Expert judgment 2. Data gathering (brainstorming, interviews, focus groups, questionnaires and surveys, benchmarking) 3. Data analysis (document analysis) 4. Decision making (voting, autocratic decision making, multicriteria decision analysis) 5. Data representation (affinity diagrams, mind mapping) 6. Interpersonal and team skills (nominal group technique, observation/conversation, facilitation) 7. Context diagram 8. Prototypes
5.2. Collect Requirements: outputs | 1. Requirements documentation 2. Requirements traceability matrix
5.3. Define Scope: inputs | 1. Project charter 2. Project management plan (scope management plan) 3. Project documents (assumption log, requirements documentation, risk register) 4. Enterprise environmental factors 5. Organizational process assets
5.3. Define Scope: tools and techniques | 1. Expert judgment 2. Data analysis (alternatives analysis) 3. Decision making (multicriteria decision making) 4. Interpersonal and team skills (facilitation) 5. Product analysis
5.3. Define Scope: outputs | 1. Project scope statement 2. Project documents update (assumption log, requirements documentation, requirements traceability matrix, stakeholder register)
5.4. Create WBS: inputs | 1. Project management plan (scope management plan) 2. Project documents (project scope statement, requirements documentation) 3. Enterprise environmental factors 4. Organizational process assets
5.4. Create WBS: tools and techniques | 1. Expert judgment 2. Decomposition
5.4. Create WBS: outputs | 1. Scope baseline 2. Project documents updates (assumption log, requirements documentation)
5.5. Validate Scope: inputs | 1. Project management plan (scope management plan, requirements management plan, scope baseline) 2. Project documents (lessons learned register, quality reports, requirements documentation, requirements traceability matrix) 3. Verified deliverables 4. Work performance data
5.5. Validate Scope: tools and techniques | 1. Inspection 2. Decision making (voting)
5.5. Validate Scope: outputs | 1. Accepted deliverables 2. Work performance information 3. Change requests 4. Project document updates (lessons learned register, requirements documentation, requirements traceability matrix)
5.6. Control Scope: inputs | 1. Project management plan (scope management plan, requirements management plan, change management plan, configuration management plan, scope baseline, performance measurement baseline) 2. Project documents (lessons learned register, requirements documentation, requirements traceability matrix) 3. Work performance data 4. Organizational process assets
5.6. Control Scope: tools and techniques | 1. Data analysis (variance analysis, trend analysis)
5.6. Control Scope: outputs | 1. Work performance information 2. Change requests 3. Project management plan updates (scope management plan, scope baseline, schedule baseline, cost baseline, performance measurement baseline) 4. Project documents updates (lessons learned register, requirements documentation, requirements traceability matrix)
6. Project Schedule Management: processes | 6.1. Plan schedule management 6.2. Define activities 6.3. Sequence activities 6.4. Estimate activity durations 6.5. Develop schedule 6.6. Control schedule
6.1. Plan Schedule Management: inputs | 1. Project charter 2. Project management plan 3. Enterprise environmental factors 4. Organizational process assets
6.1. Plan Schedule Management: tools and techniques | 1. Expert judgment 2. Data analysis 3. Meetings
6.1. Plan Schedule Management: outputs | 1. Schedule management plan
6.2. Define Activities: inputs | 1. Project management plan 2. Enterprise environmental factors 3. Organizational process assets
6.2. Define Activities: tools and techniques | 1. Expert judgment 2. Decomposition 3. Rolling wave planning 4. Meetings
6.2. Define Activities: outputs | 1. Activity list 2. Activity attributes 3. Milestone list 4. Change requests 5. Project management plan updates
6.3. Sequence Activities: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
6.3. Sequence Activities: tools and techniques | 1. Precedence diagramming method 2. Dependency determination and integration 3. Leads and lags 4. Project management information system
6.3. Sequence Activities: outputs | 1. Project schedule network diagrams 2. Project documents updates
6.4. Estimate Activity Durations: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
6.4. Estimate Activity Durations: tools and techniques | 1. Expert judgment 2. Analogous estimating 3. Parametric estimating 4. Three-point estimating 5. Bottom-up estimating 6. Data analysis 7. Decision making 8. Meetings
6.4. Estimate Activity Durations: outputs | 1. Duration estimates 2. Basis of estimates 3. Project documents updates
6.5. Develop Schedule: inputs | 1. Project management plan 2. Project documents 3. Agreements 4. Enterprise environmental factors 5. Organizational process assets
6.5. Develop Schedule: tools and techniques | 1. Schedule network analysis 2. Critical path method 3. Resource optimization 4. Data analysis 5. Leads and lags 6. Schedule compression 7. Project management information system 8. Agile release planning
6.5. Develop Schedule: outputs | 1. Schedule baseline 2. Project schedule 3. Schedule data 4. Project calendars 5. Change requests 6. Project management plan updates 7. Project documents updates
6.6. Control Schedule: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Organizational process assets
6.6. Control Schedule: tools and techniques | 1. Data analysis 2. Critical path method 3. Project management information system 4. Resource optimization 5. Leads and lags 6. Schedule compression
6.6. Control Schedule: outputs | 1. Work performance information 2. Schedule forecasts 3. Change requests 4. Project management plan updates 5. Project documents updates
7. Project Cost Management: processes | 7.1. Plan cost management 7.2. Estimate costs 7.3. Determine budget 7.4. Control costs
7.1. Plan Cost Management: inputs | 1. Project charter 2. Project management plan 3. Enterprise environmental factors 4. Organizational process assets
7.1. Plan Cost Management: tools and techniques | 1. Expert judgment 2. Data analysis 3. Meetings
7.1. Plan Cost Management: outputs | 1. Cost management plan
7.2. Estimate Costs: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
7.2. Estimate Costs: tools and techniques | 1. Expert judgment 2. Analogous estimating 3. Parametric estimating 5. Bottom-up estimating 6. Data analysis 7. Project management information system 8. Decision making
7.2. Estimate Costs: outputs
7.3. Determine Budget: inputs
7.3. Determine Budget: tools and techniques
7.3. Determine Budget: outputs
7.4. Control Costs: inputs
7.4. Control Costs: tools and techniques
7.4. Control Costs: outputs
8. Project Quality Management: processes | 8.1. Plan quality management 8.2. Manage quality 8.3. Control quality
8.1. Plan Quality Management: inputs
8.1. Plan Quality Management: tools and techniques
8.1. Plan Quality Management: outputs
8.2. Manage Quality: inputs
8.2. Manage Quality: tools and techniques
8.2. Manage Quality: outputs
8.3. Control Quality: inputs
8.3. Control Quality: tools and techniques
8.3. Control Quality: outputs
9. Project Resource Management: processes | 9.1. Plan resource management 9.2. Estimate activity resources 9.3. Acquire resources 9.4. Develop team 9.5. Manage team 9.6. Control resources
9.1. Plan Resource Management: inputs
9.1. Plan Resource Management: tools and techniques
9.1. Plan Resource Management: outputs
9.2. Estimate Activity Resources: inputs
9.2. Estimate Activity Resources: tools and techniques
9.2. Estimate Activity Resources: outputs
9.3. Acquire Resources: inputs
9.3. Acquire Resources: tools and techniques
9.3. Acquire Resources: outputs
9.4. Develop Team: inputs
9.4. Develop Team: tools and techniques
9.4. Develop Team: outputs
9.5. Manage Team: inputs
9.5. Manage Team: tools and techniques
9.5. Manage Team: outputs
9.6. Control Resources: inputs
9.6. Control Resources: tools and techniques
9.6. Control Resources: outputs
10. Project Communications Management: processes | 10.1. Plan communications management 10.2. Manage communications 10.3. Monitor communications
10.1. Plan Communications Management: inputs
10.1. Plan Communications Management: tools and techniques
10.1. Plan Communications Management: outputs
10.2. Manage Communications: inputs
10.2. Manage Communications: tools and techniques
10.2. Manage Communications: outputs
10.3. Monitor Communications: inputs
10.3. Monitor Communications: tools and techniques
10.3. Monitor Communications: outputs
11. Project Risk Management: processes | 11.1. Plan risk management 11.2. Identify risks 11.3. Perform qualitative risk analysis 11.4. Perform quantitative risk analysis 11.5. Plan risk responses 11.6. Implement risk responses 11.7. Monitor risks
11.1. Plan Risk Management: inputs
11.1. Plan Risk Management: tools and techniques
11.1. Plan Risk Management: outputs
11.2. Identify Risks: inputs
11.2. Identify Risks: tools and techniques
11.2. Identify Risks: outputs
11.3. Perform Qualitative Risk Analysis: inputs
11.3. Perform Qualitative Risk Analysis: tools and techniques
11.3. Perform Qualitative Risk Analysis: outputs
11.4. Perform Quantitative Risk Analysis: inputs
11.4. Perform Quantitative Risk Analysis: tools and techniques
11.4. Perform Quantitative Risk Analysis: outputs
11.5. Plan Risk Responses: inputs
11.5. Plan Risk Responses: tools and techniques
11.5. Plan Risk Responses: outputs
11.6. Implement Risk Responses: inputs
11.6. Implement Risk Responses: tools and techniques
11.6. Implement Risk Responses: outputs
11.7. Monitor Risks: inputs
11.7. Monitor Risks: tools and techniques
11.7. Monitor Risks: outputs
12. Project Procurement Management: processes | 12.1. Plan procurement management 12.2. Conduct procurements 12.3. Control procurements
12.1. Plan Procurement Management: inputs
12.1. Plan Procurement Management: tools and techniques
12.1. Plan Procurement Management: outputs
12.2. Conduct Procurements: inputs
12.2. Conduct Procurements: tools and techniques
12.2. Conduct Procurements: outputs
12.3. Control Procurements: inputs
12.3. Control Procurements: tools and techniques
12.3. Control Procurements: outputs
13. Project Stakeholder Mangement: processes | 13.1. Identify stakeholders 13.2. Plan stakeholder engagement 13.3. Manage stakeholder engagement 13.4. Monitor stakeholder engagement
13.1. Identify Stakeholders: inputs
13.1. Identify Stakeholders: tools and techniques
13.1. Identify Stakeholders: outputs
13.2. Plan Stakeholder Engagement: inputs
13.2. Plan Stakeholder Engagement: tools and techniques
13.2. Plan Stakeholder Engagement: outputs
13.3. Manage Stakeholder Engagement: inputs
13.3. Manage Stakeholder Engagement: tools and techniques
13.3. Manage Stakeholder Engagement: outputs
13.4. Monitor Stakeholder Engagement: inputs
13.4. Monitor Stakeholder Engagement: tools and techniques
13.4. Monitor Stakeholder Engagement: outputs