## Sheet1
Side 1 | Side 2 | Category
4. Project Integration Management: processes | 4.1. Develop project charter 4.2. Develop project management plan 4.3. Direct and manage project work 4.4. Manage project knowledge 4.5. Monitor and control project work 4.6. Perform integrated change control 4.7. Close project or phase
4.1. Develop Project Charter: inputs | 1. Business documents 2. Agreements 3. Enterprise environmental factors 4. Organizational process assets
4.1. Develop Project Charter: tools and techniques | 1. Expert judgment 2. Data gathering 3. Interpersonal and team skills 4. Meetings
4.1. Develop Project Charter: outputs | 1. Project charter 2. Assumption log
4.2. Develop Project Management Plan: inputs | 1. Project charter 2. Outputs from other processes 3. Enterprise environmental factors 4. Organizational process assets
4.2. Develop Project Management Plan: tools and techniques | 1. Expert judgment 2. Data gathering 3. Interpersonal and team skills 4. Meetings
4.2. Develop Project Management Plan: outputs | 1. Project management plan
4.3. Direct and Manage Project Work: inputs | 1. Project management plan 2. Project documents 3. Approved change requests 4. Enterprise environmental factors 5. Organizational process assets
4.3. Direct and Manage Project Work: tools and techniques | 1. Expert judgment 2. Project management information system 3. Meetings
4.3. Direct and Manage Project Work: outputs | 1. Deliverables 2. Work performance data 3. Issue log 4. Change requests 5. Project management plan updates 6. Project documents updates 7. Organizational process assets updates
4.4. Manage Project Knowledge: inputs | 1. Project management plan 2. Project documents 3. Deliverables 4. Enterprise environmental factors 5. Organizational process assets
4.4. Manage Project Knowledge: tools and techniques | 1. Expert judgment 2. Knowledge management 3. Information management 4. Interpersonal and team skills
4.4. Manage Project Knowledge: outputs | 1. Lessons learned register 2. Project management plan updates 3. Organizational process assets updates
4.5. Monitor and Control Project Work: inputs | 1. Project management plan 2. Project documents 3. Work performance information 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets
4.5. Monitor and Control Project Work: tools and techniques | 1. Expert judgment 2. Data analysis 3. Decision making 4. Meetings
4.5. Monitor and Control Project Work: outputs | 1. Work performance reports 2. Change requests 3. Project management plan updates 4. Project documents updates
4.6. Perform Integrated Change Control: inputs | 1. Project management plan 2. Project documents 3. Work performance reports 4. Change requests 5. Enterprise environmental factors 6. Organizational process assets
4.6. Perform Integrated Change Control: tools and techniques | 1. Expert judgment 2. Change control tools 3. Data analysis 4. Decision making 5. Meetings
4.6. Perform Integrated Change Control: outputs | 1. Approved change requests 2. Project management plan updates 3. Project documents updates
4.7. Close Project or Phase: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Accepted deliverables 5. Business documents 6. Agreements 7. Procurement documentation 8. Organizational process assets
4.7. Close Project or Phase: tools and techniques | 1. Expert judment 2. Data analysis 3. Meetings
4.7. Close Project or Phase: outputs | 1. Project documents updates 2. Final product, service, or result transition 3. Final report 4. Organizational process assets updates
5. Project Scope Management: processes | 5.1. Plan scope management 5.2. Collect requirements 5.3. Define scope 5.4. Create WBS 5.5. Validate scope 5.6. Control scope
5.1. Plan Scope Management: inputs | 1. Project charter 2. Project management plan 3. Enterprise and environmental factors 4. Organizational process assets
5.1. Plan Scope Management: tools and techniques | 1. Expert judgment 2. Data analysis 3. Meetings
5.1. Plan Scope Management: outputs | 1. Scope management plan 2. Requirements management plan
5.2. Collect Requirements: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Business documents 5. Agreements 6. Enterprise environmental factors 7. Organizational process assets
5.2. Collect Requirements: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Decision making 5. Data representation 6. Interpersonal and team skills 7. Context diagram 8. Prototypes
5.2. Collect Requirements: outputs | 1. Requirements documentation 2. Requirements traceability matrix
5.3. Define Scope: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Enterprise environmental factors 5. Organizational process assets
5.3. Define Scope: tools and techniques | 1. Expert judgment 2. Data analysis 3. Decision making 4. Interpersonal and team skills 5. Product analysis
5.3. Define Scope: outputs | 1. Project scope statement 2. Project documents update
5.4. Create WBS: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
5.4. Create WBS: tools and techniques | 1. Expert judgment 2. Decomposition
5.4. Create WBS: outputs | 1. Scope baseline 2. Project documents updates
5.5. Validate Scope: inputs | 1. Project management plan 2. Project documents 3. Verified deliverables 4. Work performance data
5.5. Validate Scope: tools and techniques | 1. Inspection 2. Decision making
5.5. Validate Scope: outputs | 1. Accepted deliverables 2. Work performance information 3. Change requests 4. Project document updates
5.6. Control Scope: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Organizational process assets
5.6. Control Scope: tools and techniques | 1. Data analysis
5.6. Control Scope: outputs | 1. Work performance information 2. Change requests 3. Project management plan updates 4. Project documents updates
6. Project Schedule Management: processes | 6.1. Plan schedule management 6.2. Define activities 6.3. Sequence activities 6.4. Estimate activity durations 6.5. Develop schedule 6.6. Control schedule
6.1. Plan Schedule Management: inputs | 1. Project charter 2. Project management plan 3. Enterprise environmental factors 4. Organizational process assets
6.1. Plan Schedule Management: tools and techniques | 1. Expert judgment 2. Data analysis 3. Meetings
6.1. Plan Schedule Management: outputs | 1. Schedule management plan
6.2. Define Activities: inputs | 1. Project management plan 2. Enterprise environmental factors 3. Organizational process assets
6.2. Define Activities: tools and techniques | 1. Expert judgment 2. Decomposition 3. Rolling wave planning 4. Meetings
6.2. Define Activities: outputs | 1. Activity list 2. Activity attributes 3. Milestone list 4. Change requests 5. Project management plan updates
6.3. Sequence Activities: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
6.3. Sequence Activities: tools and techniques | 1. Precedence diagramming method 2. Dependency determination and integration 3. Leads and lags 4. Project management information system
6.3. Sequence Activities: outputs | 1. Project schedule network diagrams 2. Project documents updates
6.4. Estimate Activity Durations: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
6.4. Estimate Activity Durations: tools and techniques | 1. Expert judgment 2. Analogous estimating 3. Parametric estimating 4. Three-point estimating 5. Bottom-up estimating 6. Data analysis 7. Decision making 8. Meetings
6.4. Estimate Activity Durations: outputs | 1. Duration estimates 2. Basis of estimates 3. Project documents updates
6.5. Develop Schedule: inputs | 1. Project management plan 2. Project documents 3. Agreements 4. Enterprise environmental factors 5. Organizational process assets
6.5. Develop Schedule: tools and techniques | 1. Schedule network analysis 2. Critical path method 3. Resource optimization 4. Data analysis 5. Leads and lags 6. Schedule compression 7. Project management information system 8. Agile release planning
6.5. Develop Schedule: outputs | 1. Schedule baseline 2. Project schedule 3. Schedule data 4. Project calendars 5. Change requests 6. Project management plan updates 7. Project documents updates
6.6. Control Schedule: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Organizational process assets
6.6. Control Schedule: tools and techniques | 1. Data analysis 2. Critical path method 3. Project management information system 4. Resource optimization 5. Leads and lags 6. Schedule compression
6.6. Control Schedule: outputs | 1. Work performance information 2. Schedule forecasts 3. Change requests 4. Project management plan updates 5. Project documents updates
7. Project Cost Management: processes | 7.1. Plan cost management 7.2. Estimate costs 7.3. Determine budget 7.4. Control costs
7.1. Plan Cost Management: inputs | 1. Project charter 2. Project management plan 3. Enterprise environmental factors 4. Organizational process assets
7.1. Plan Cost Management: tools and techniques | 1. Expert judgment 2. Data analysis 3. Meetings
7.1. Plan Cost Management: outputs | 1. Cost management plan
7.2. Estimate Costs: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
7.2. Estimate Costs: tools and techniques | 1. Expert judgment 2. Analogous estimating 3. Parametric estimating 5. Bottom-up estimating 6. Data analysis 7. Project management information system 8. Decision making
7.2. Estimate Costs: outputs | 1. Cost estimates 2. Basis of estimates 3. Project documents updates
7.3. Determine Budget: inputs | 1. Project management plan 2. Project documents 3. Business documents 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets
7.3. Determine Budget: tools and techniques | 1. Expert judgment 2. Cost aggregation 3. Data analysis 4. Historical information review 5. Funding limit reconciliation 6. Financing
7.3. Determine Budget: outputs | 1. Cost baseline 2. Project funding requirements 3. Project documents updates
7.4. Control Costs: inputs | 1. Project management plan 2. Project documents 3. Project funding requirements 4. Work performance data 5. Organizational process assets
7.4. Control Costs: tools and techniques | 1. Expert judgment 2. Data analysis 3. To-complete performance index 4. Project management information system
7.4. Control Costs: outputs | 1. Work performance information 2. Cost forecasts 3. Change requests 4. Project management plan updates 5. Project documents updates
8. Project Quality Management: processes | 8.1. Plan quality management 8.2. Manage quality 8.3. Control quality
8.1. Plan Quality Management: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Enterprise environmental factors 5. Organizational process assets
8.1. Plan Quality Management: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Decision making 5. Data representation 6. Test and inspection planning 7. Meetings
8.1. Plan Quality Management: outputs | 1. Quality management plan 2. Quality metrics 3. Project management plan updates 4. Project documents updates
8.2. Manage Quality: inputs | 1. Project management plan 2. Project documents 3. Organizational process assets
8.2. Manage Quality: tools and techniques | 1. Data gathering 2. Data analysis 3. Decision making 4. Data representation 5. Audits 6. Design for X 7. Problem solving 8. Quality improvement methods
8.2. Manage Quality: outputs | 1. Quality reports 2. Test and evaluation documents 3. Change requests 4. Project management plan updates 5. Project documents updates
8.3. Control Quality: inputs | 1. Project management plan 2. Project documents 3. Approved change requests 4. Deliverables 5. Work performance data 6. Enterprise environmental factors 7. Organizational process assets
8.3. Control Quality: tools and techniques | 1. Data gathering 2. Data analysis 3. Inspection 4. Testing/product evaluations 5. Data representation 6. Meetings
8.3. Control Quality: outputs | 1. Quality control measurements 2. Verified deliverables 3. Work performance information 4. Change requests 5. Project management plan updates 6. Project documents updates
9. Project Resource Management: processes | 9.1. Plan resource management 9.2. Estimate activity resources 9.3. Acquire resources 9.4. Develop team 9.5. Manage team 9.6. Control resources
9.1. Plan Resource Management: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Enterprise environmental factors 5. Organizational process assets
9.1. Plan Resource Management: tools and techniques | 1. Expert judgment 2. Data representation 3. Organizational theory 4. Meetings
9.1. Plan Resource Management: outputs | 1. Resources management plan 2. Team charter 3. Project documents updates
9.2. Estimate Activity Resources: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
9.2. Estimate Activity Resources: tools and techniques | 1. Expert judgment 2. Bottom-up estimating 3. Analogous estimating 4. Parametric estimating 5. Data analysis 6. Project management information system 7. Meetings
9.2. Estimate Activity Resources: outputs | 1. Resource requirements 2. Basis of estimates 3. Resource breakdown structure 4. Project documents updates
9.3. Acquire Resources: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
9.3. Acquire Resources: tools and techniques | 1. Decision making 2. Interpersonal and team skills 3. Pre-assignment 4. Virtual teams
9.3. Acquire Resources: outputs | 1. Physical resource assignments 2. Project team assignments 3. Resource calendars 4. Change requests 5. Project management plan updates 6. Project documents updates 7. Enterprise environmental factors updates 8. Organizational process assets updates
9.4. Develop Team: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
9.4. Develop Team: tools and techniques | 1. Colocation 2. Virtual teams 3. Communication technology 4. Interpersonal and team skills 5. Recognition and rewards 6. Training 7. Individual and team assessments 8. Meetings
9.4. Develop Team: outputs | 1. Team performance assessments 2. Change requests 3. Project management plan updates 4. Project documents updates 5. Enterprise environmental factors updates 6. Organizational process assets updates
9.5. Manage Team: inputs | 1. Project management plan 2. Project documents 3. Work performance reports 4. Team performance assessments 5. Enterprise environmental factors 6. Organizational process assets
9.5. Manage Team: tools and techniques | 1. Interpersonal and team skills 2. Project management information system
9.5. Manage Team: outputs | 1. Change requests 2. Project management plan updates 3. Project documents updates 4. Enterprise environmental factors updates
9.6. Control Resources: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Agreements 5. Organizational process assets
9.6. Control Resources: tools and techniques | 1. Data analysis 2. Problem solving 3. Interpersonal and team skills 4. Project management information system
9.6. Control Resources: outputs | 1. Work performance information 2. Change requests 3. Project management plan updates 4. Project documents updates
10. Project Communications Management: processes | 10.1. Plan communications management 10.2. Manage communications 10.3. Monitor communications
10.1. Plan Communications Management: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Enterprise environmental factors 5. Organizational process assets
10.1. Plan Communications Management: tools and techniques | 1. Expert judgment 2. Communication requirements analysis 3. Communication technology 4. Communication models 5. Communication methods 6. Interpersonal and team skills 7. Data representation 8. Meetings
10.1. Plan Communications Management: outputs | 1. Communications management plan 2. Project management plan updates 3. Project documents update
10.2. Manage Communications: inputs | 1. Project management plan 2. Project documents 3. Work performance reports 4. Enterprise environmental factors 5. Organizational process assets
10.2. Manage Communications: tools and techniques | 1. Communication technology 2. Communication methods 3. Communication skills 4. Project management information system 5. Project reporting 6. Interpersonal and team skills 7. Meetings
10.2. Manage Communications: outputs | 1. Project communications 2. Project management plan updates 3. Project documents updates 4. Organizational process assets updates
10.3. Monitor Communications: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Enterprise environmental factors 5. Organizational process assets
10.3. Monitor Communications: tools and techniques | 1. Expert judgment 2. Project management information system 3. Data representation 4. Interpersonal and team skills 5. Meetings
10.3. Monitor Communications: outputs | 1. Work performance information 2. Change requests 3. Project management plan updates 4. Project documents updates
11. Project Risk Management: processes | 11.1. Plan risk management 11.2. Identify risks 11.3. Perform qualitative risk analysis 11.4. Perform quantitative risk analysis 11.5. Plan risk responses 11.6. Implement risk responses 11.7. Monitor risks
11.1. Plan Risk Management: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Enterprise environmental factors 5. Organizational process assets
11.1. Plan Risk Management: tools and techniques | 1. Expert judgment 2. Data analysis 3. Meetings
11.1. Plan Risk Management: outputs | 1. Risk management plan
11.2. Identify Risks: inputs | 1. Project management plan 2. Project documents 3. Agreements 4. Procurement documentation 5. Enterprise environmental factors 6. Organizational process assets
11.2. Identify Risks: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Interpersonal and team skills 5. Prompt lists 6. Meetings
11.2. Identify Risks: outputs | 1. Risk register 2. Risk report 3. Project documents updates
11.3. Perform Qualitative Risk Analysis: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
11.3. Perform Qualitative Risk Analysis: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Interpersonal and team skills 5. Risk categorization 6. Data representation 7. Meetings
11.3. Perform Qualitative Risk Analysis: outputs | 1. Project documents updates
11.4. Perform Quantitative Risk Analysis: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
11.4. Perform Quantitative Risk Analysis: tools and techniques | 1. Expert judgment 2. Data gathering 3. Interpersonal and team skills 4. Representations of uncertainty 5. Data analysis
11.4. Perform Quantitative Risk Analysis: outputs | 1. Project documents updates
11.5. Plan Risk Responses: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
11.5. Plan Risk Responses: tools and techniques | 1. Expert judgment 2. Data gathering 3. Interpersonal and team skills 4. Strategies for threats 5. Strategies for opportunities 6. Contingent response strategies 7. Strategies for overall project risk 8. Data analysis 9. Decision making
11.5. Plan Risk Responses: outputs | 1. Change requests 2. Project management plan updates 3. Project documents updates
11.6. Implement Risk Responses: inputs | 1. Project management plan 2. Project documents 3. Organizational process assets
11.6. Implement Risk Responses: tools and techniques | 1. Expert judgment 2. Interpersonal and team skills 3. Project management information system
11.6. Implement Risk Responses: outputs | 1. Change requests 2. Project documents updates
11.7. Monitor Risks: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Work performance reports
11.7. Monitor Risks: tools and techniques | 1. Data analysis 2. Audits 3. Meetings
11.7. Monitor Risks: outputs | 1. Work performance information 2. Change requests 3. Project management plan updates 4. Project documents updates 5. Organizational process assets updates
12. Project Procurement Management: processes | 12.1. Plan procurement management 12.2. Conduct procurements 12.3. Control procurements
12.1. Plan Procurement Management: inputs | 1. Project charter 2. Business documents 3. Project management plan 4. Project documents 5. Enterprise environmental factors 6. Organizational process assets
12.1. Plan Procurement Management: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Source selection analysis 5. Meetings
12.1. Plan Procurement Management: outputs | 1. Procurement management plan 2. Procurement strategy 3. Bid documents 4. Procurement statement of work 5. Source selection criteria 6. Make-or-buy decisions 7. Independent cost estimates 8. Change requests 9. Project documents updates 10. Organizational process assets updates
12.2. Conduct Procurements: inputs | 1. Project management plan 2. Project documents 3. Procurement documentation 4. Seller proposals 5. Enterprise environmental factors 6. Organizational process assets
12.2. Conduct Procurements: tools and techniques | 1. Expert judgment 2. Advertising 3. Bidder conferences 4. Data analysis 5. Interpersonal and team skills
12.2. Conduct Procurements: outputs | 1. Selected sellers 2. Agreements 3. Change requests 4. Project management plan updates 5. Project documents updates 6. Organizational process assets updates
12.3. Control Procurements: inputs | 1. Project management plan 2. Project documents 3. Agreements 4. Procurement documentation 5. Approved change requests 6. Work performance data 7. Enterprise environmental factors 8. Organizational process assets
12.3. Control Procurements: tools and techniques | 1. Expert judgment 2. Claims administration 3. Data analysis 4. Inspection 5. Audits
12.3. Control Procurements: outputs | 1. Closed procurements 2. Work performance information 3. Procurement documentation updates 4. Change requests 5. Project management plan updates 6. Project documents updates 7. Organizational process assets updates
13. Project Stakeholder Mangement: processes | 13.1. Identify stakeholders 13.2. Plan stakeholder engagement 13.3. Manage stakeholder engagement 13.4. Monitor stakeholder engagement
13.1. Identify Stakeholders: inputs | 1. Project charter 2. Business documents 3. Project management plan 4. Project documents 5. Agreements 6. Enterprise environmental factors 7. Organizational process assets
13.1. Identify Stakeholders: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Data representation 5. Meetings
13.1. Identify Stakeholders: outputs | 1. Stakeholder register 2. Change requests 3. Project management plan updates 4. Project documents updates
13.2. Plan Stakeholder Engagement: inputs | 1. Project charter 2. Project management plan 3. Project documents 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets
13.2. Plan Stakeholder Engagement: tools and techniques | 1. Expert judgment 2. Data gathering 3. Data analysis 4. Decision making 5. Data representation 6. Meetings
13.2. Plan Stakeholder Engagement: outputs | 1. Stakeholder engagement plan
13.3. Manage Stakeholder Engagement: inputs | 1. Project management plan 2. Project documents 3. Enterprise environmental factors 4. Organizational process assets
13.3. Manage Stakeholder Engagement: tools and techniques | 1. Expert judgment 2. Communication skills 3. Interpersonal and team skills 4. Ground rules 5. Meetings
13.3. Manage Stakeholder Engagement: outputs | 1. Change requests 2. Project management plan updates 3. Project documents updates
13.4. Monitor Stakeholder Engagement: inputs | 1. Project management plan 2. Project documents 3. Work performance data 4. Enterprise environmental factors 5. Organizational process assets
13.4. Monitor Stakeholder Engagement: tools and techniques | 1. Data analysis 2. Decision making 3. Data representation 4. Communication skills 5. Interpersonal and team skills 6. Meetings
13.4. Monitor Stakeholder Engagement: outputs | 1. Work performance information 2. Change requests 3. Project management plan updates 4. Project documents updates